## Sheet1
PMP Study Material from PMChamp.com
Legend | Process Name | Based on PMBOK Guide Fourth Edition
Inputs
Tools & Techniques
Outputs
| Initiating | Planning | Executing | Monitoring & Controlling | Closing
Project Integration Management | Develop Project Charter | Develop Project Management Plan | Direct and Manage Project Execution | Monitor and Control Project Work | Close Project or Phase
| Project Statement of Work | Project Charter | Project Management Plan | Project Management Plan | Project Management Plan
| Business Case | Planning Outputs | Approved Change Requests | Performance Reports | Accepted Deliverables
| Contract | EEF & OPA | EEF & OPA | EEF & OPA | EEF & OPA
EEF & OPA
| Expert Judgement | Expert Judgement | Expert Judgement | Expert Judgement | Expert Judgement
Information Systems
| Project Charter | Project Management Plan | Deliverables | Change Requests | Final product or service transition
|  |  | Work Performance Information | Project Management Plan updates | OPA updates
|  |  | Change Requests | Project Document Updates
Project Management Plan updates
Project Document Updates
Perform Integrated Change Control
Project Management Plan
Work Performance Information
Change Requests
EEF & OPA
Expert Judgement
Change Control Meetings
Change Request status updates
Project Management Plan updates
Project Document Updates
Project Scope Management |  | Collect Requirements |  | Verify Scope
|  | Project Charter |  | Project Management Plan
|  | Stakeholder Register |  | Requirements Documentation
Requirements Traceability Matrix
Validated deliverables
|  | Interviews |  | Inspection
Focus Groups
Facilitated workshops
Group Creativity techniques
Group decision making techniques
Questionnaires and Surveys
Observations
Prototypes
|  | Requirements Documentation |  | Accepted Deliverables
|  | Requirements Management Plan |  | Change Requests
|  | Requirements Traceability Matrix |  | Project document updates
|  | Define Scope |  | Control Scope
|  | Project Charter |  | Project Management Plan
|  | Requirements Documentation |  | Requirements Documentation
|  | OPA |  | Requirements Traceability Matrix
Work Performance Information
OPA
|  | Expert Judgement |  | Variance Analysis
Product Analysis
Alternatives identification
Facilitated Workshops
|  | Project Scope Statement |  | Work performance measurements
|  | Project Document updates |  | OPA updates
Change Requests
Project Management Plan updates
Project document updates
Create WBS
Project Scope Statement
Requirements Documentation
OPA
Decomposition
WBS
WBS Dictionary
Scope Baseline
Project Document updates
Project Time Management |  | Define Activities |  | Control Schedule
|  | Scope Baseline |  | Project Management Plan
|  | EEF & OPA |  | Project Schedule
Work Performance information
OPA
|  | Decomposition |  | Performance reviews
|  | Rolling wave planning |  | Variance analysis
|  | Templates |  | Project Management Software
|  | Expert Judgement |  | Resource Levelling
What-if scenario
Adjusting leads and lags
Schedule compression
Scheduling tool
|  | Activity List |  | Work Performance measurements
|  | Activity attributes |  | OPA updates
|  | Milestone List |  | Change Requests
Project Management Plan updates
Project document updates
Sequence Activities
Activity List
Activity attributes
Milestone List
Project Scope Statement
OPA
Precedence Diagramming (PDM)
Dependency determination
Applying leads and lags
Schedule network templates
Project Schedule network diagrams
Project document updates
Estimate Activity Resources
Activity List
Activity attributes
Resource calendars
EEF & OPA
Expert Judgement
Alternative Analysis
Published estimating data
Bottom-up estimating
Project Management Software
Activity Resource requirements
Resource breakdown structure
Project document updates
Estimate Activity durations
Activity List
Activity attributes
Activity Resource requirements
Resource calendars
Project Scope Statement
EEF & OPA
Expert Judgement
Analogous estimating
Parametric estimating
Three-point estimates (PERT)
Reserve Analysis
Activity duration estimates
Project document updates
Develop Schedule
Activity List
Activity attributes
Resource calendars
Project Scope Statement
Project Schedule network diagrams
Activity Resources requirements
Activity duration estimates
EEF & OPA
Schedule network analysis
Critical path method
Critical chain method
Resource levelling
What-if scenario analysis
Applying leads and lags
Schedule compression
Scheduling tool
Project schedule
Schedule baseline
Schedule data
Project document updates
Project Cost Management |  | Estimate Costs |  | Control Costs
|  | Scope Baseline |  | Project Management Plan
|  | Project Schedule |  | Project funding requirements
|  | Human Resource plan |  | Work performance information
|  | Risk register |  | OPA
EEF & OPA
|  | Expert Judgement |  | Earned Value Management (EVM)
|  | Analogous estimating |  | Forecasting
|  | Parametric estimating |  | To-complete performance index
|  | Bottom-up estimating |  | Performance reviews
|  | Three-point estimates |  | Variance analysis
|  | Reserve analysis |  | Project Management software
Cost of quality
Estimating software
Vendor bid analysis
|  | Activity cost estimates |  | Work performance measurements
|  | Basis of estimates |  | Budget forecasts
|  | Project document updates |  | OPA updates
Change requests
Project management plan updates
Project document updates
Determine Budget
Activity cost estimates
Basis of estimates
Scope Baseline
Project schedule
Resource calendars
Contracts
OPA
Cost aggregation
Reserve analysis
Expert Judgement
Historical relationships
Funding limit reconciliation
Cost performance baseline
Project funding requirements
Project document updates
Project Quality Management |  | Plan Quality | Perform Quality Assurance | Perform Quality Control
|  | Scope Baseline | Project Management plan | Project Management plan
|  | Stakeholder register | Quality metrics | Quality metrics
|  | Cost performance baseline | Work performance information | Quality checklists
|  | Schedule baseline | Quality control measurements | Work performance measurements
|  | Risk register |  | Approved change requests
|  | EEF & OPA |  | Deliverables
OPA
|  | Cost-benefit analysis | Plan quality | Cause and effect diagrams
|  | Cost of quality | Perform quality control T&T | Control charts
|  | Control charts | Quality audits | Flowcharting
|  | Benchmarking | Process analysis | Histogram
|  | Design of experiments |  | Pareto chart
|  | Statistical sampling |  | Run chart
|  | Flowcharting |  | Scatter diagram
|  | Propreitary QM methodologies |  | Statistical sampling
|  | Additional quality planning tools |  | Inspection
Approved change requests review
|  | Quality management plan | OPA updates | Quality control measurements
|  | Quality metrics | Change requests | Validated changes
|  | Quality checklists | Project Management plan updates | Validated deliverables
|  | Process improvement plan | Project document updates | OPA updates
|  | Project document updates |  | Change requests
Project Management plan updates
Project document updates
Project Human Resources Management |  | Develop Human Resource Plan | Acquire Project Team
|  | Activity resource requirements | Project Management plan
|  | EEF & OPA | EEF & OPA
|  | Organization charts | Pre-assignment
|  | Position descriptions | Negotiation
|  | Networking | Acquisition
|  | Organization theory | Virtual teams
|  | Human Resource plan | Project staff assignments
Resource calendars
Project Management plan updates
Develop Project Team
Project staff assignments
Project Management plan
Resource calendars
Interpersonal skills
Training
Team building activities
Ground rules
Co-location
Recognition and reward
Team performance assessments
EEF updates
Manage Project Team
Project staff assignments
Project management plan
Team performance assessments
Performance reports
OPA
Observation and conversation
Project performance appraisals
Conflict Management
Issue log
Interpersonal skills
OPA & EEF updates
Change requests
Project management plan updates
Project Communications Management | Identify Stakeholders | Plan Communications | Distribute Information | Report Performance
| Project charter | Stakeholder register | Project Management plan | Project Management plan
| Procurement documents | Stakeholder Management strategy | Performance reports | Work performance information
| EEF & OPA | EEF & OPA | OPA | Work performance measurements
Budget forecasts
OPA
| Stakeholder Analysis | Communication reqments analysis | Communication methods | Variance analysis
| Expert judgement | Communication technology | Information distribution tools | Forecasting methods
|  | Communication models |  | Communication methods
|  | Communication methods |  | Reporting systems
| Stakeholder Register | Communication management plan | OPA updates | Performance reports
| Stakeholder Management strategy | Project document updates |  | OPA updates
Change requests
Manage Stakeholder Expectations
Stakeholder register
Stakeholder Management strategy
Project Management plan
Issue log
Change log
OPA
Communication methods
Interpersonal skills
Management skills
OPA updates
Change requests
Project Management plan updates
Project document updates
Project Risk Management |  | Plan Risk Management |  | Monitor and Control Risks
|  | Project scope statement |  | Risk register
|  | Cost Management plan |  | Project Management plan
|  | Schedule Management plan |  | Work performance information
|  | Communication management plan |  | Performance reports
EEF & OPA
|  | Planning meetings and analysis |  | Risk re-assessment
Risk audits
Variance and trend analysis
Technical performnce measuremnt
Reserve analysis
Status meetings
|  | Risk Management plan |  | Risk register updates
OPA updates
Change requests
Project Management plan updates
Project document updates
Identify Risks
Risk Management plan
Activity cost estimates
Activity duration estimates
Scope baseline
Stakeholder register
Cost Management plan
Schedule Management plan
Quality management plan
Project documents
EEF & OPA
Documentation reviews
Information gathering techniques
Checklist analysis
Assumptions analysis
Diagramming techniques
SWOT analysis
Expert judgement
Risk register
Perform Qualitative Risk Analysis
Risk Register
Risk Management plan
Project Scope statement
OPA
Risk probability and impact assessments
Probability and Impact matrix
Risk data quality assessments
Risk categorization
Risk urgency assessment
Expert judgement
Risk register updates
Perform Quantitative Risk Analysis
Risk register
Risk Management plan
Cost Management plan
Schedule Management plan
OPA
Data gathering and representation techniques
Quantitative risk analysis and modeling techniques
Expert judgement
Risk register updates
Plan Risk Responses
Risk register
Risk Management plan
Strategies for negative risks
Strategies for positive risks
Contingent response strategies
Expert judgement
Risk register updates
Risk related contract decisions
Project Management plan updates
Project document updates
Project Procurement Management |  | Plan Procurements | Conduct Procurement | Administer Procurements | Close Procurement
|  | Scope baseline | Project Management plan | Procurement documents | Project Management plan
|  | Requirements documentation | Procurement documents | Project Management plan | Procurement documentation
|  | Teaming agreements | Source selection criteria | Contract
|  | Risk register | Qualified seller list | Performance reports
|  | Risk related contract decisions | Seller proposals | Approved change requests
|  | Activity resource requirements | Project documents | Work performance information
|  | Project schedule | Make-or-buy decision
|  | Activity cost estimates | Teaming agreements
|  | Cost performance baseline | OPA
EEF & OPA
|  | Make or buy analysis | Bidder conferences | Contract change control system | Procurement audits
|  | Expert judgement | Proposal evaluation techniques | Procurement performance reviews | Negotiated settlements
|  | Contract types | Independent estimates | Inspection and audits | Records Management system
|  |  | Expert judgement | Performance reporting
|  |  | Advertising | Payment systems
|  |  | Internet search | Claims administration
|  |  | Procurement negotiations | Records Management system
|  | Procurement management plan | Selected sellers | Procurement documentation | Closed procurement
|  | Procurement statement of work | Procurement contract award | OPA updates | OPA updates
|  | Make-or-buy decision | Resource calendars | Change requests
|  | Procurement documents | Change requests | Project Management plan updates
|  | Source Selection criteria | Project Management plan updates
|  | Change requests | Project document updates